## Slide 1
CFMWS Nine Levers of Scope - Implementation Timeline
DEV - Development | TEST - System Integration Test | UAT - User Acceptance Testing | PROD - Production | CNV - Data Conversion | TTT - Train The Trainer | CRP - Conference Room Pilot | Go-Live
Workstream / Lever | Jul 25 | Sep 25 | Nov 25 | Jan 26 | Mar 26 | May 26 | Jul 26 | Sep 26 | Nov 26 | Jan 27 | Mar 27 | May 27 | Jul 27 | Sep 27 | Nov 27
Lever 1 - Software Scope | █ | █ | █ | █ | █ | █ | █ |  |  |  |  |  |  |  | 
Lever 2 - Process Scope | █ | █ | █ | █ | █ | █ | █ |  |  |  |  |  |  |  | 
Lever 3 - Organization | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | █
Lever 4 - Enhancements | █ | █ | █ | █ | █ | █ | █ |  |  |  |  |  |  |  | 
Lever 5 - Infrastructure |  |  | DEV |  |  | TEST / UAT | PROD |  |  |  |  |  |  |  | 
Lever 6 - Interfaces | █ | █ | █ | █ | █ | █ | █ |  |  |  |  |  |  |  | 
Lever 7 - Data Conversion |  |  |  |  | CNV1 | CNV2 | █ | █ | █ | █ | CNV3 | █ | █ | █ | CNV4
Lever 8 - Reports | █ | █ | █ | █ | █ | █ | █ |  |  |  |  |  |  |  | 
Lever 9 - Implementation Phase 1 | █ | █ | █ | █ | █ | █ | Go-Live P1 |  |  |  |  |  |  |  | 
Lever 9 - Implementation Phase 2 |  |  |  |  | █ | █ | █ | █ | █ | █ | █ | █ | █ | █ | Go-Live P2