## Slide 1: Plan on a Page
CRP – Conference Room Pilot | CNV – Conversion Cycles | TTT – Train The Trainer | SIT – System Integration Testing | UAT – User Acceptance Testing
 |  |  |  | 2027 |  |  |  |  |  |  |  |  |  |  |  | 2028 |  |  |  |  | 
SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN
Go Live
Go Live
TTT
Rel 27 A
Rel 27B
Quarterly Oracle Releases 
CRP1
Scope & Timeline Re-evaluation
CNV1
SIT
UAT
CNV2
Discovery & Process Workshops
Build & Config
Payroll Testing
Cutover
Rel 27C
Rel 27D
Rel 28A
Rel 28B
CNV3
CNV4
CRP2
US
UK
Discovery & Integrated
Design
Co-Execute
Co-Operate
Hypercare
Co-Execute
Co-Operate
Hypercare
Delta CNV
After our discussion, we have reworked the proposed timeline to have both the US and UK Go Live in January 2028, an 18-month plan.
TTT
CRP1
CNV1
SIT
UAT
Build & Config
Payroll Testing
Cutover
CNV3
CRP2
Delta CNV
Change Strategy
Readiness Assessment
Communications Plan
Change Impact Analysis
Adoption Engmt
Stakeholder Matrix
CNV4
CNV2