## The Nine Levers of Scope

IBM uses a methodology referred to as “The Nine Levers of Scope” to define project implementation scope. It segregates total project implementation scope into nine discrete components identified below. These levers define the considerations & assumptions used for planning and estimating Oracle Cloud implementation project for CFMWS (Canadian Forces Morale and Welfare Services).

Our scope considerations, assumptions and estimates are based on IBM’s current understanding of the requirements and information made available to IBM at this point of time. Deviations that arise during the proposed engagement will be managed through the change control process and may result in adjustments to the project scope, estimated schedule, charges, and other terms.

The parties acknowledge and agree that COVID-19 is an event beyond the parties’ reasonable control, and it is not possible to foresee (or advisable to try and foresee) its duration, impact or extent (including measures and recommendations that may be put in place by regulators). As such, where a party's non-monetary obligations are not performed, affected, and/or delayed and that is attributable to COVID-19 or its related impacts, notwithstanding any other provision in the agreement, the affected party will not be responsible for such non-performance, affected performance or delay. The parties will act reasonably to discuss the affected obligations, potential workarounds and related issues in good faith and will document any agreed changes to the agreement.

Levers of scope

### Lever 1 – Software Scope

|  | The Software Scope lever defines Oracle products/modules which will be implemented as part of Chicago Public School’s proposed Oracle Cloud implementation. |
| --- | --- |

The following software and modules are in scope of the Oracle HCM Transformation project:

| Part Number | Oracle Pack Name (SaaS) | Oracle Sub Modules (SaaS) | Release |
| --- | --- | --- | --- |

| B85800 | Oracle Fusion Human Capital Management Base Cloud Service | Global Human Resources | P1 |
| --- | --- | --- | --- |
|  |  | Onboarding | P1 |
|  |  | Benefits | P1 |
|  |  | Absence Management | P1 |
| B87675 | Oracle Fusion Recruiting Cloud Service | Recruiting | P2 |
| B109620 | Oracle Fusion Workforce Compensation Cloud Service | Workforce Compensation | P1 |
| B87388 | Oracle Fusion Human Resource Help Desk Cloud Service | HR Help Desk | P2 |
| B86335 | Oracle Fusion Payroll Cloud Service for Canada | Canada Payroll | P1 |
| B75365 | Oracle Fusion Time and Labor Cloud Service | Time and Labor | P1 |
| B94925 | Oracle Fusion Talent Management Cloud Service | Talent Management | P2 |
| B85242 | Oracle Fusion Learning Cloud Service | Learning | P2 |
| B89482 | Oracle Fusion Workforce Health and Safety Incidents Cloud Service | Health and Safety | P2 |
| B98207 | Oracle Fusion Workforce Scheduling Cloud Service | Workforce Scheduling | P1 |
| B92354 | Oracle Fusion HCM Analytics | HCM Analytics | P2 |
| B95763 | Oracle Fusion Recruiting Booster Cloud Service | Recruiting Booster | P2 |

- Overall Software Scope Considerations

The latest released version of Oracle Fusion Cloud Applications before the start of the project will be considered in this proposal.

During Common Design phase, if it is found that some new modules will be required to be configured, such requirements will be managed in accordance with the change control process.

IBM does not warrant the functionality of the in-scope Oracle Cloud modules. IBM will work with Oracle Corporation (product vendor) on behalf of CFMWS in resolving problems related to the software. CFMWS must have appropriate agreements with Oracle for such support.

- Out of Scope

Any upgrade or modifications of existing legacy applications.

Following modules mentioned in BOM not considered for implementation as there are no business requirements mentioned in the RFP

HCM (Advanced HCM Controls, HCM Communicate, Touch points, Workforce Labor Optimization)

### Lever 2 – Process Scope

|  | The Process Scope lever defines the business process areas that are in scope for this project. Process Scope encompasses business processes that are intended to exist in production. |
| --- | --- |

The business process flows will be reviewed at the beginning of the project. IBM along with CFMWS will assess fitment of the business flows with those of standard out of box Oracle cloud products.

The following business processes are in scope for this engagement:

In Scope Oracle Business Processes

| Functional Area (Level 2) | Detailed Process (Level 3) |
| --- | --- |
| Core HR | Manage Workforce Structures Manage Workforce Lifecycle Manage Employment Information Manage Promotion, Transfer & Termination Manage Workforce Records Manage Employee Relations Manage Union Data Maintain Worker Directories |
| 2010: Manage Absences | 201001: Maintain Absence Enrolments Manage Absence Processing Report and Analyse Absence Data Schedule and Record Absences |
| Benefits | Manage Benefits Manage Benefit Plans, Programs and Events Manage Benefit Rates and coverages Manage Elements Maintain Benefit Enrolment Elect Benefits Manage Life Event |
| Compensation | Manage Workforce Compensation Administer Workforce Compensation Manage Base Pay Manage Compensation Budgets Manage Compensation Survey Manage Individual Compensation Manage Personal Contributions Manage Total Compensation Statement |
| Time & Labor | Record standard time and overtime Report Time Transfer Time Approve Time Analyze Time Manage Worker Schedules Manage Time Entry Rules and Calculations Manage Eligibility Profiles |
| Payroll | Configure Payroll legislation Configure Consolidation Groups and Payroll Configure Payroll Entities Setup Pay rules Maintain Personal Payroll Information Manage Pay Manage Payroll Transaction Confirm Payroll Readiness Calculate, Validate and Balance Payroll Calculate Payment Distribution Calculate Cost Distribution Distribute Payroll Payments Distribute Payroll Accounting Information Manage Regulatory and Tax Reporting(Canada) Costing information |
| Goal & Performance Management, Talent & Succession Management (Talent Management) | Define Organizational Goals and Measurements Assess Workforce Competencies Configure Organizational Development Plans. Define Carrier Development plans Review Talent Plan Succession Manage Talent Profiles Establish Worker Goals Manage Goals Evaluate Worker Performance Manage Performance Improvement Plan Manage Individual Development Plan Analyze Workforce Development Performance |
| Learning | Manage Learning Programs Aline Learning programs with competency. Manage Learning Curriculums Configure Learning Certificates Manage Learner Enrolment and Completion |
| Recruiting & Onboarding | Source and Manage Candidates Manage Job Requisition Lifecycle Manage Candidates Manage Job Offers Manage Candidate Lifecycle |
| HR Help Desk | Enable the HR Help Desk Profile Options Configure SLA's Manage Cases (Grievances) Enable Help Desk Resolutions |
| Health and Safety | Manage Safety Incidents Manage Safety Inspections Create Employee Self-Service Incidents |

Overall Process Scope Considerations

IBM will use Blueworks Live Process Modeler for baselining Oracle Fusion business process flows based on CFMWS specific requirements

It is considered that CFMWS will adopt standard process, workarounds supported by cloud and avoid PaaS extensions as far as possible.

A Fit-Gap Analysis will be performed during Design phase and options evaluated. If the proposed solution requires a new process, module, tool or customization, it will be managed per the agreed project change control process.

CFMWS will primarily adopt out of the box features in Oracle Cloud HCM to the maximum extent feasible without compromising regulatory or compliance requirements. If a regulatory or compliance gap is identified which may require an Oracle PaaS solution or extension, the need for custom development will go through change control process.

Oracle out of box security roles and profiles will be configured. IBM has assumed configuration of up to ten (10) custom roles across all modules in scope.

- Core HR - Configure 1 Enterprise Structure, Configure Hire to Retire processes delivered with Oracle HCM Cloud and setup ESS and MSS, Configure up to 2 Journeys (Onboarding & Offboarding). Delivered Oracle security roles for modules in scope

- Absence – Configure up to 13 Absence Plans (Accrual, Paternity, Parental, Maternity, Sick, Sabbatical, Compassionate, Medical, Jury Duty, Personal, Bereavement, Critical illness, Unpaid/LOA), Workflow Approvals to be configured.

- Learning- Configure 10 Learning Plans, Learning content creation not in scope, Branding customization not in scope

- Recruiting – Configure up to 2 Candidate Selection Workflows, 2 Career Sites (For Internal and External EEs), 2 offer letter templates.

- Benefits – Configure 1 Program,8 plans and plan types with 9 options,30 Benefits Rates and 8 coverages

- Talent and Performance -Configure up to 2 Performance templates (Annual & Mid-Year Review), 2 Goal Plans (Executive & Others)

- Compensation –2 Salary Basis (1 for Yearly and 1 for Hourly),2 Compensation Plan (one for Salary Review plan and one for Bonus calculation), Load Market survey data to calculate the Pay Equities, Up to 10 Individual Compensation plans, Up to 10 Elements for Compensations,2 Compensation Statement

- Time and Labor – 1 web clock and 2 Time-cards Layout, 10 Time Entry and Time Calculation rules, Workflow Approvals to be configured and 1 Journey (if needed for shifts change communication)

- Payroll

    - Oracle’s own tax Engine for Canada (CAPTE) to be used for taxation updates

    - Payroll for Canada Legislation as delivered by payroll to be fully implemented

    - Payrolls like Semi-monthly/ Biweekly to be processed

    - Employee Taxes CPP/ EI to be processed

    - Absence module in Oracle HCM Cloud would be implemented for recording Absences (Vacation, unpaid leave etc.) and integrating with Payroll

    - Assuming approx. 100-150 custom elements may have to be configured, around 2 TRUs, with each LE being its own Tax reporting Unit/ Payroll Statutory Unit

    - Standard Payroll/ Statutory reports as provide by oracle would suffice in most scenarios

    - Most Workflow Approvals would have to be custom configured

    - Quebec State is applicable as a Work location and regulatory/taxation differences are applicable

    - The IBM proposed HCM solution will process retroactive payments only for employees and periods that it ran payroll for. Retro calculations for periods prior to system go-live, and for employees that it didn't calculate payroll for, are out of scope.

    - Payroll for the locally engaged German employees (approximately 40) German employees who are not paid under Canadian taxation rules, will continue to be done by a local German company and not within this Oracle Cloud HCM system. Interfaces and/or data exchanges between this system and the local German payroll company are not in scope.

Out of Scope

Any process or functionality not explicitly listed to be in-scope, is Out of Scope

### Lever 3 – Organization Scope

|  | The Organization Scope lever defines the project’s impact on the organization and end-users, and outlines the change management activities included in the scope of the project. |
| --- | --- |

Project Primary Location: Canada

Application Language: English & French

Project Implementation Language: English

Number of countries to implement: Three (3)

Number of Employees: 5,300 plus 2,000 former employees to access historical pay information

All Deliverables, documentation, communication, training materials/instruction guides will be in English only

Overall scope: Change Management, HR Strategy, Training ***TBC whether we change OCM/HR to advisory

Training approach: Instructor Led, Self-paced, Train-the-Trainer, Oracle Guided Learning

In Scope Change Management, HR Strategy and Training  (Phases 1 & 2):

- Change Management

** if removed, we will only provide OCM advisory services

All OCM content will be developed in English only

Conduct up to 15 stakeholder interviews with HR and Business SMEs/users

IBM will develop the change strategy, develop communication materials and readiness assessments CFMWS is responsible for developing and executing other change related activities for example: engagement with end users (Change Agent Network), distributing communications, analyzing readiness assessment data, executing mitigating actions to drive adoption of the new solution

IBM will gather Change Impacts; CFMWS will be responsible for iterating on the change impacts and mitigating actions.

- Training

The CFMWS Training lead will be two-in-a-box resource and be responsible for collaborating with IBM OCM/Training lead for the Training program

IBM will develop the Training Strategy and Plan, including conducting a Training Needs Analysis

After the Fit-Gap Analysis has been performed during Design phase and options evaluated, and if the proposed solution requires a new process, module, tool or customization, we will need to re-evaluate the training scope and it will be managed per the agreed project change control process.

The Training Strategy and plan will outline the plan for sustainment, meeting the needs for any maintain and support ongoing training needs. (NFR184)

Training curriculum will be signed off before the training developers will begin content development.

Oracle Guided Learning (OGL) portal will be used for all eLearning, workflows, user manuals

Training development assumes 10 to 15 slides of Instructor Led materials (for Introduction deck for TTT. One per module. MS PPT – 10-15 slides) will be developed in English only.  ** Farida – will we assume this translates to 1 hr per ILT?

CFMWS is responsible for translating training materials

French translated training materials will be packaged together by the IBM Training team

CFMWS is responsible for publishing courses to the Learning Management System (LMS) **Farida, should include verbiage such assuming publishing to the DLN in phase 1 and possibly to their LMS in phase 2

IBM Training Team will develop 50 job aids (20-25 steps maximum) shared between phases 1 and 2 and mapped to delta processes only ** how many are we doing, this needs to align to the table below

IBM will conduct two Train-the-Trainer (TTT) sessions, one in each phase (1 and 2); these sessions will be conducted in English ** Farida, should include something around answering questions in FR?

TTT will cover Oracle module introduction training (10-15) slides and hands-on-exercises for delta processes only ** This needs to be clearer

In summary, IBM training effort assumes the following breakdown of content; hours/effort can be moved between products:

| Training Package | English Only | French |
| --- | --- | --- |
| Oracle Guided Learning (OGL) | Work instructions, self-paced training materials and tips | x |
| Instructor-led-Training | Introduction deck for TTT. MS PPT – 10-15 slides | x |
| Job Aids | 40 job aids shared between Phase 1 & 2 mapped to process | x |
| Training Environment | Hands on exercises for delta processes only |  |
| Train-the-Trainer | Deliver TTT in English to 10-15 CFMWS Trainers with module overview ppt and delta exercises only |  |

CFMWS will provide 10-15 Trainers to attend and participate in TTT

IBM Functional Team and CFMWS SMEs will support training development and reviews (15% of their work effort is dedicated to support training scope)

IBM Functional Team will set-up the training environment used for TTT (i.e. data requirements, training IDs. etc.)

CFMWS is responsible for conducting end user training delivery

IBM Functional team will conduct demos and Knowledge Transfer session for complex content to CFMWS selected roles **We need to discuss this with Henry to ensure alignment

The CFMWS is responsible for any external training/certification requirements (as required)

The CFMWS Training lead will be responsible for handling unionized requirements (e.g. scheduling, training needs, etc...)

CFMWS is responsible for scheduling training and training logistics coordination including training invitations/communications and equipment

The training program will be transitioned to CFMWS upon completion of TTT

- HR Strategy

HR Assessment: IBM to conduct a review of CFMWS’ internal HR organizational structure and provide recommendations for the future organization aligned to the proposed solution.

HR Assessment is designed to surface competencies, capabilities, functions and operational principles centered around the Employee Experience. HR Assessment output will provide recommendations on Service Delivery, Skills and Capabilities, Employee Experience, Operating Model.

Options:

HR Transformation strategy? (Susan’s note for Rosita to review) Leveraging IBM’s patented Component Business Model IBM would design and deliver an interactive workshop with HR and business leaders to understand the current state of the employee hire to retire cycle, identify alignment on strategic imperatives and create a Roadmap to focus on now, soon and later operational opportunities

Conducting training sessions for payroll & HR employees to ensure full system proficiency prior to launch of the new solution, and ongoing refresher and new functionality training after launch.

Out of Scope ** OCM and HR Strategy TBC

End User Training

Execution of change activities outside of developing the change strategy, communication materials and change readiness assessment

Publishing content to the CFMWS Learning Management System

HR processes re-engineering and process mapping, org design, capabilities/proficiency assessment

### Lever 4 – Enhancements Scope

|  | The Enhancement Scope lever defines the process extensions included in the scope of the project |
| --- | --- |

In Scope

Overall Enhancement Scope Considerations

Workflow approvals will be configured using business rules in the Business Process Management (BPM) approval management engine of fusion cloud. ‘Out-of-the-box’ functionalities offered in Oracle Cloud Services and available workaround solutions will be sufficient to map all the business requirements. The scope of this lever will be validated during the discovery phase.

In Scope

To support HCM functionality for CFMWS, we have considered the following number of fast formulas

| Enhancement Type (Fast Formula) | Low | Medium | High | Total |
| --- | --- | --- | --- | --- |
| Benefits | 3 | 1 | 1 | 5 |
| Absence Management | 4 | 2 | 2 | 8 |
| Compensation | 3 | 4 | 1 | 8 |
| Payroll | 12 | 6 | 5 | 23 |
| Time and Labor | 3 | 2 | 1 | 6 |
|  | 25 | 15 | 10 | 50 |

| RICEW ID | Requirement ID | Module | Complexity |
| --- | --- | --- | --- |
| EXT001 | Absence Entry Validation Maternity Leave | Absence | M |
| EXT002 | Absence Entry Validation Paternity Leave | Absence | M |
| EXT003 | Absence Duration | Absence | H |
| EXT004 | Absence Carryover | Absence | H |
| EXT005 | Leave Accrual Calc | Absence | M |
| EXT006 | Absence Eligibility | Absence | L |
| EXT007 | Absence Eligibility | Absence | L |
| EXT008 | Absence Eligibility | Absence | L |
| EXT009 | Absence Entry Validation for PTO Leave | Absence | L |
| EXT010 | Absence Entry Validation for Sick Leave | Absence | L |
| EXT011 | Determine Benefit Cost Calculation | Benefit | H |
| EXT012 | Adjust Benefit Contribution | Benefit | M |
| EXT013 | Benefit Enrolment & Amendments | Benefit | L |
| EXT014 | Calculate Benefit Eligibility | Benefit | L |
| EXT015 | Calculate Benefit Eligibility | Benefit | L |
| EXT016 | Salary Calculation | Compensation | L |
| EXT017 | Bonus Eligibility | Compensation | L |
| EXT018 | Pay Adjustment | Compensation | H |
| EXT019 | Overtime Calculation | Compensation | M |
| EXT020 | Deduction Calculation | Compensation | M |
| EXT021 | PayGrade Assignment | Compensation | M |
| EXT022 | Compensation Plan | Compensation | L |
| EXT023 | Compensation Plan | Compensation | L |
| EXT024 | Time Entry Rules | OTL | L |
| EXT025 | Time Calculation Rules | OTL | L |
| EXT026 | Record Employee Time Data | OTL | H |
| EXT027 | Time Calculation Rules | OTL | M |
| EXT028 | CFMWS Payroll deductions Processing | Payroll | M |
| EXT029 | Splits deductions Over two Pay Processing | Payroll | M |
| EXT030 | split of pay into multiple general ledger | Payroll | M |
| EXT031 | Rounding rules based on pay group | Payroll | M |
| EXT032 | Assigns employees to specific pay groups | Payroll | M |
| EXT033 | Custom Retro Calculation | Payroll | H |
| EXT034 | Custom Federal Tax Calculation | Payroll | H |
| EXT035 | Custom Provincial Tax Calc: | Payroll | H |
| EXT036 | Custom Deduction Priority | Payroll | H |
| EXT037 | Custom Deduction Scheduling | Payroll | M |
| EXT038 | Custom Retro Payroll Rollover | Payroll | H |
| EXT039 | Custom FT Preferred Tax Deduction | Payroll | M |
| EXT040 | Custom Non Preferred Tax Deduction | Payroll | L |
| EXT041 | Collect payroll Data | Payroll | L |
| EXT042 | Collect payroll Data | Payroll | L |
| EXT043 | Validate Payroll Elements Input | Payroll | L |
| EXT044 | Validate Payroll Elements Input | Payroll | L |
| EXT045 | Process Payroll | Payroll | L |
| EXT046 | Process Payroll | Payroll | L |
| EXT047 | Process Payroll | Payroll | L |
| EXT048 | Process Payroll | Payroll | L |
| EXT049 | Process Payroll | Payroll | L |
| EXT050 | Validate Payroll Elements Input | Payroll | L |

Out of Scope

No PaaS / Bolt-on extension have been included as part of this solution. During Work Package A, if any gaps are identified, which requires PaaS development then additional effort will be estimated and priced in accordance with the agreed change control process.

### Lever 5 – Technical Infrastructure Scope

|  | The Technical Infrastructure Scope lever defines the hardware, software, and networks required to support the Oracle Cloud Services for CFMWS in accordance with the agreed project schedule. |
| --- | --- |

Overall Infrastructure Considerations

- The technical infrastructure will be delivered and supported by Oracle and is considered to be sized accordingly to meet all performance related requirements of CFMWS. Oracle will be the Hosting Partner and provide the infrastructure and DBA support for SaaS solution.

- All patching and upgrade related activities for the SaaS applications will be performed/managed by Oracle. Impact assessment of changes by Oracle patches and any changes required due to the impact of Oracle patches will be subject Change Request.

- Performance Testing or Performance Tuning of standard Oracle product/functionality will be responsibility of Oracle. Any issues related to performance, security, maintenance, and availability of the cloud applications will be Oracle’s responsibility. In case of any adverse system performance related to standard Oracle functionality, IBM will interlock with Oracle to get the fix, but Oracle will be solely responsible for it.

- If performance issue is reported on any custom functionality developed by IBM during testing, IBM will take the responsibility to fix the issue to the extent issue is traced to IBM development standards. IBM has not considered any separate performance testing phase for this project.

- At a minimum, the following environments will be required to support the project: Development,  Test, Payroll Testing, Training and 1 Production will be required for the life of the project.  These environments should be ready per the dates which will be provided in the agreed project plan Additional instances may be required on a temporary basis for training etc. and will be detailed as part of the instance strategy.

- CFMWS will provision bandwidth for internet connectivity required for accessing Cloud applications. IBM will have no responsibility for set-up of internal computing environment, including such items as installation of networking software, Internet software and connection, etc. This will be the CFMWS responsibility.

- IBM considers that a dedicated secured area or closed shop workspace is not required at this moment for offshore resources in India for accessing CFMWS’s network. IBM will work with CFMWS during the start of the project to validate this assumption. If any such dedicated secured area access is required to be setup for offshore, it will be managed with the agreed PCR process.

In Scope

- DEV (start of <October> <2025>): This environment will be used for configuration, developing Reports, Interfaces, Conversion, Extensions (RICE) objects, and unit testing.

- TEST (start of <February> <2026>): This environment will be used as a fully system integrated environment for end-to-end system integration testing (SIT) and user acceptance (UAT) testing. This environment will also be intermittently used as the training environment and will require significant planning and coordination.

- UAT (start of <May> <2026>): This environment will be used to conduct User Acceptance Testing (UAT).

- PROD (start of <June> <2026>): This environment will be used as the Enterprise Production environment.

- All SaaS and PaaS environments will be available as per the identified Project schedule.

Out of Scope

Disaster Recovery (DR) and Business Continuity (BC) related activities for Oracle SaaS, PaaS and any other CFMWS applications is not scope of this implementation.

### Lever 6 – Interface Scope

|  | Interface Scope lever defines the interfaces needed to support the integration of the systems required by the proposed solution. |
| --- | --- |

|  |  | Complexity |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| PHASE | Type | L | M | H | Total | Grand Total |
| PHASE1 | Outbound | 5 | 6 | 1 | 12 | 15 |
|  | Inbound | 0 | 1 | 2 | 3 |  |
|  | Total | 5 | 7 | 3 | 15 |  |
| PHASE2 | Outbound | 2 | 3 | 0 | 5 | 7 |
|  | Inbound | 0 | 0 | 2 | 2 |  |
|  | Total | 2 | 3 | 2 | 7 |  |
| Grand Total |  | 7 | 9 | 6 |  | 21 |

The interface scope for Oracle HCM Cloud includes the following integrations:

| RICEW ID | Interface Name | Source System | Target System | Complexity | PHASE |
| --- | --- | --- | --- | --- | --- |
| INT001 | Benefits-Feed to Canada Life | Oracle Cloud HCM | Canada Life(Benefits) | Medium | PHASE1 |
| INT002 | Demographic Feed to iBoutique | Oracle Cloud HCM | Seasons/iBoutique | Medium | PHASE1 |
| INT003 | Employee Information to LinkedIn | Oracle Cloud HCM | Linkedin Learning | Medium | PHASE2 |
| INT004 | EE - Demographics to DLN | Oracle Cloud HCM | DLN(CSOD SBX) | Medium | PHASE2 |
| INT005 | EE – Demographics to EFAP | Oracle Cloud HCM | Dialogue(EFAP) | Low | PHASE2 |
| INT006 | Aon Pension Admin | Oracle Cloud HCM | Aon(Pension Admin) | Medium | PHASE1 |
| INT007 | LifeWorks (RTWSP) | Oracle Cloud HCM | LifeWorks(RTWSP) | Medium | PHASE1 |
| INT008 | Health and Safety Information—Interim | Oracle Cloud HCM | SMAAT Paratox Jobarix | Low | PHASE2 |
| INT009 | GL Interface (Oracle Fin) | Oracle Cloud HCM | PROPHET(Oracle FIN) | High | PHASE1 |
| INT010 | Demographic Feed -Marcom-Unily | Oracle Cloud HCM | CORE(Marcom-Unily) | Medium | PHASE1 |
| INT011 | Bring Back Employee Info | Linkedin Learning | Oracle HCM | High | PHASE2 |
| INT012 | Job Posting Feed | Oracle Cloud HCM | Job Posting | Low | PHASE1 |
| INT013 | Employee ID Updated | Oracle HCM | Active Directory | Low | PHASE1 |
| INT014 | Account Id Update | Active Directory | Oracle HCM | Medium | PHASE1 |
| INT015 | INBOUND FROM Canex | Canex Credit Plan | Oracle Cloud HCM | High | PHASE1 |
| INT016 | EE Demographic - Interim | Oracle Cloud HCM | Talent Management System | Low | PHASE1 |
| INT017 | EE Demographic - Interim | Oracle Cloud HCM | Learning Management System | Low | PHASE1 |
| INT018 | EE Demographic - Interim | Oracle Cloud HCM | Case Management | Low | PHASE1 |
| INT019 | Performance Rating -Interim | Talent Management | Oracle Cloud HCM | High | PHASE1 |
| INT020 | To create Micro-Learnings in HCM | Third Party Learning System | Oracle Cloud HCM | High | PHASE2 |
| INT021 | Outbound to Third Party Survey vendor | Oracle Cloud HCM | Third Party Survey Vendor | Medium | PHASE2 |
| INT022 | Employee Demographics | Oracle Cloud HCM | IBM Analytics | Medium | PHASE1 |

- In Scope

Oracle Integration Cloud and Oracle Database Cloud Service will be used as Middleware platform for all the integrations.

- Definitions of interface complexity are as follows:

- Low: These integrations involve standard APIs or out-of-the-box integrations with minimal or no customization.

- Medium: These integrations may require some customization or configuration. They might require more complex data mapping or transformation but still use standard Oracle SaaS integration tools.

- High: These integrations may require complex customization, data transformation, or multiple system interactions. They may require more advanced technical skills and may need additional middleware components or custom development.

Oracle Integration Cloud would be the integration platform for the exchange & consumption of data between the Oracle Cloud and 3rd party applications.

For all Inbound integrations, the data will be processed and transformed in OIC Middleware layer. Post processing, the data will be received at Oracle Cloud as per the specified format and structure compatible to Oracle Cloud.

For all outbound integrations, the data will be shared as available in Oracle Cloud. The extracted data will be processed and transformed in OIC Middleware. Post processing, OIC will send data to as per the format/type required by the 3rd party systems.

As per design phase outcome, it will be decided if Error Management for integration will be handled by out of the box Error Management pack included in Oracle Integration Cloud which serves the following activities – search & display errors, resubmit errors, view instance, view audit trails etc. There is no separate Error management framework been considered for integration.

HCM Extracts and BIP would be leveraged to extract data from Oracle SaaS Cloud.

### Lever 7 – Data Conversion Scope

|  | The Data Conversion Scope lever defines the conversion strategy and identifies those conversions that will be required to transition to the target environment. |
| --- | --- |

In accordance with the RFP specifications and modules in scope for implementation, the below list identifies the conversions in scope of the implementation.

Below is the list of Oracle Fusion Cloud HCM conversion Items:

List of In-Scope Data Co

| RICEW ID | Data Entity | In-Scope | Out of Scope | Source | Target | Type | Complexity | Phase |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CNV-1 | Department |  |  | Accero | Global Human Resources | HDL | Low | PHASE1 |
| CNV-2 | Position |  |  | Accero | Global Human Resources | HDL | Medium | PHASE1 |
| CNV-3 | Person Data |  |  | Accero | Global Human Resources | HDL | Medium | PHASE1 |
| CNV-4 | Assignment Data |  |  | Accero | Global Human Resources | HDL | High | PHASE1 |
| CNV-5 | Work Relationships |  |  | Accero | Global Human Resources | HDL | Medium | PHASE1 |
| CNV-6 | Action, Action Reason |  |  | Accero | Global Human Resources | HDL | Low | PHASE1 |
| CNV-7 | Grade, Grade Rate, Grade Ladder |  |  | Accero | Global Human Resources | HDL | Medium | PHASE1 |
| CNV-8 | Job, Job Family |  |  | Accero | Global Human Resources | HDL | Medium | PHASE1 |
| CNV-9 | Organization Unions |  |  | Accero | Global Human Resources | HDL | High | PHASE1 |
| CNV-10 | Rating Model |  |  | MyTalent | Talent Management | HDL | Low | PHASE2 |
| CNV-11 | Education Establishment |  |  | MyTalent | Talent Management | HDL | Low | PHASE2 |
| CNV-12 | Competencies |  |  | MyTalent | Talent Management | HDL | Medium | PHASE2 |
| CNV-13 | Performance Rating History |  |  | MyTalent | Talent Management | HDL | Low | PHASE2 |
| CNV-14 | Goals |  |  | MyTalent | Talent Management | HDL | Medium | PHASE2 |
| CNV-15 | Element Entry - Compensation |  |  | Accero | Compensation | HDL | Low | PHASE1 |
| CNV-16 | Salary Details |  |  | Accero | Compensation | HDL | Medium | PHASE1 |
| CNV-17 | Time reporter Data |  |  | Accero | Time & Labor | HDL | Medium | PHASE1 |
| CNV-18 | Enrollment Data |  |  | Accero | Benefits | HDL | Medium | PHASE1 |
| CNV-19 | Rates |  |  | Accero | Benefits | HDL | Low | PHASE1 |
| CNV-20 | Balances |  |  | Accero | Benefits | HDL | Medium | PHASE1 |
| CNV-21 | Beneficiaries/Dependents |  |  | Accero | Benefits | HDL | Medium | PHASE1 |
| CNV-22 | Absence Plans |  |  | Accero | Absence Management | HDL | Medium | PHASE1 |
| CNV-23 | Absence accruals Balances |  |  | Accero | Absence Management | HDL | High | PHASE1 |
| CNV-24 | Candidate Profile |  |  | Accero | Recruitment | HDL | High | PHASE2 |
| CNV-25 | Open Job Requisitions |  |  | Accero | Recruitment | HDL | High | PHASE2 |
| CNV-26 | Payment Methods |  |  | Accero | Payroll | HDL | Medium | PHASE1 |
| CNV-27 | Pay Element Entry |  |  | Accero | Payroll | HDL | Medium | PHASE1 |
| CNV-28 | Pay Balances |  |  | Accero | Payroll | HDL | High | PHASE1 |
| CNV-29 | Accumulators |  |  | Accero | Payroll | HDL | High | PHASE1 |
| CNV-30 | Bank and Direct Deposit Information |  |  | Accero | Payroll | HDL | Medium | PHASE1 |
| CNV-31 | SCROM Content Import |  |  | Accero | Global Human Resources | HDL | Medium | PHASE1 |

List of In-Scope Data Conversion Items

CFMWS will perform the extraction, transformation at source and cleansing of data from source system.

CFMWS will be responsible to identify the data sources for all the elements identified as per the data conversion strategy.

IBS will assist CFMWS in identification of data set for extraction, finalizing the data transformation and data cleansing rules.

IBM will provide the cloud data load templates and CFMWS will populate the templates with as per transformation rules

IBM team will be responsible for loading the data and reconciling the data loaded into the Oracle SaaS environments.

CFMWS will be responsible for data validation

CFMWS will provide IT systems personnel that have detailed data / systems knowledge that will be required for the gathering of data specific requirements, reviewing data conversion reports, and assisting in the cleansing of data issues.

Accero and My Talent are the only legacy systems that are considered in scope for IBM’s data conversion.

Up to 3 conversion cycles, for each application, are included in scope. These are proposed as initial conversion to facilitate configuration and build activities in the system and including validation of conversion process. Conversion run prior to the integration testing, and another prior to user acceptance of the application. A mock conversion before the cutover, the final conversion will be for the production go-live during cut-over phase.

Out of Scope

Archiving of legacy application data or even the Accero environment data is not part of the scope.

Archival of historical documents are not in scope of this implementation.

### Lever 8 – Reports Scope

|  | Reports Scope defines the reporting strategy and number of custom reports included in the scope of the project. |
| --- | --- |

During the planning phase, current production reports will be reviewed with the CFMWS business representatives to establish whether they will be required or can be rationalised / replaced by standard Fusion reports, in an effort to reduce the amount of custom report development necessary.

Cloud Reporting Capabilities

IBM has considered development effort for a total of 186 custom reports to be delivered through Oracle Cloud applications for the project. These efforts are including development, testing and deployment support.

| Application | High | Medium | Low | Total |
| --- | --- | --- | --- | --- |
| PHASE1 | 5 | 6 | 10 | 21 |
| PHASE2 | 0 | 4 | 5 | 9 |
| Total | 5 | 10 | 15 | 30 |

Following is the list of HCM Reports based on IBM’s review of the list of requirements

| RICEW ID | Report Description | Module | Complexity | PHASE |
| --- | --- | --- | --- | --- |
| REP001 | Wage allocations Report | Payroll | High | PHASE1 |
| REP002 | Payslips Cheque writer Report | Payroll | High | PHASE1 |
| REP003 | Pay Statement Report | Payroll | High | PHASE1 |
| REP004 | Wage tax categories Report | Payroll | High | PHASE1 |
| REP005 | Employee Benefit Enrollment detail report | Benefits | Medium | PHASE1 |
| REP006 | Employee Benefit Enrollment status report | Benefits | High | PHASE1 |
| REP007 | Active versus Passive Enrollment report | Benefits | Medium | PHASE1 |
| REP008 | Case Summary Report | Help Desk | Medium | PHASE1 |
| REP009 | Leave Status report | Time and Labor | Low | PHASE1 |
| REP010 | FTE Report | Time and Labor | Low | PHASE1 |
| REP011 | Utilization rates report | Time and Labor | Low | PHASE1 |
| REP012 | Employees vacant shifts report | Time and Labor | Low | PHASE1 |
| REP013 | Budget variances report | Core HR | Medium | PHASE1 |
| REP014 | Certificate/Learning expiry dates report | Learning Management | Low | PHASE1 |
| REP015 | Personal Action Update | Core HR | Low | PHASE1 |
| REP016 | Action history listing | Core HR | Low | PHASE1 |
| REP017 | Employee detailed information listing | Core HR | Low | PHASE1 |
| REP018 | New hires & terms report/ history | Core HR | Low | PHASE1 |
| REP019 | Salary History | Compensation | Low | PHASE1 |
| REP020 | Absence Accrual Report | Absence | Medium | PHASE1 |
| REP021 | Absence Entry report | Absence | Medium | PHASE1 |
| REP022 | Individual learner progress and performance details report | Learning Management | Medium | PHASE2 |
| REP023 | Job Posting Report | Recruiting | Medium | PHASE2 |
| REP024 | Job requisition Report | Recruiting | Medium | PHASE2 |
| REP025 | Hiring Manager and Candidate Details report | Recruiting | Medium | PHASE2 |
| REP026 | New Job Request and Position Details Report | Recruiting | Low | PHASE2 |
| REP027 | Health & safety incident listing | Health and Safety | Low | PHASE2 |
| REP028 | Career Training & Management - Surveys Reporting | Learning Management | Low | PHASE2 |
| REP029 | Employee Profile Report | Talent | Low | PHASE2 |
| REP030 | Help Desk Activity Report | Help Desk | Low | PHASE2 |

Overall Reporting Considerations

Out of the Box reports will be leveraged wherever available to meet the reporting requirements of CFMWS.

Multilanguage support for reporting is not in scope. The language of development will be English only.

Any additional reports discovered during Common Design phase, will be managed in accordance with the agreed PCR process.

The count and complexity of the reports will be revisited during the Common Design workshops and the effort re-baselined for reimplementation.

Out of Scope

Report development in language other than English.

### Lever 9 – Implementation Scope

|  | The Implementation lever defines the steps of the transformation lifecycle starting from business process understanding to transition to the new process and application. |
| --- | --- |

IBM proposes phased approach for implement ERP, HCM and EPM across three phases:

Phase 1: Oracle Fusion

- HCM – 13 Months Implementation

Start: July 2025

Go-Live: July 2026

Followed by 2 months of Hypercare

Phase 2: Oracle Fusion

HCM –6 months Implementation

Start: May 2026

Go-Live: Nov 2027

Followed by 1 months of Hypercare

We will leverage the IBM Oracle Rapid Move for Cloud methodology assets and accelerators throughout the implementation of the project. Some of the accelerators support the configurations to be copied from instance to instance keeping the integrity of the application setups across the instances.

IBM’s Implementation approach, timeline and estimates are based on the Oracle Cloud functionality available currently, and the currently available Future roadmap information shared by Oracle.

IBM will support CFMWS in all testing phases by providing test strategy, test scripts, troubleshooting and defect resolution.

After each phase go-live, we have considered three (3) months of Hypercare

UAT will be lead by CFMWS and IBM will support.

Out of Scope

### Other Key Assumptions

As Assumptions to the Project, the Parties agree that:

(a)	Estimates provided herein are based on the information CFMWS provided. Therefore, IBM reserves the right to adjust or amend the estimates provided in this document in the event that additional detailed information is obtained relative to CFMWS’s functional and technical business requirements. Any additional significant business requirements, material changes or previously undisclosed information may have a direct impact (increase or decrease) on the estimates documented.

(b)	IBM will rely upon the information CFMWS supplies. We assume that such information will be reliable, adequate and accurate for the purposes of the deliverables. We will not, however, independently test or verify any such information. The results of our work will be based on regulatory, financial, technological and other conditions prevailing presently.

(c)	IBM will conduct up to two three (3) Regression Test cycles to test impact of quarterly SaaS updates from Oracle during the project, limited to the Oracle application. Up to 200 hours of effort is included for each Regression Test cycle across all Cloud applications (i.e., a total of 600 hours)

(d)	Oracle, as the ERP SaaS Provider, will be responsible for fixing any defects in the Oracle Cloud applications identified during testing. If defects are not resolved by the ERP SaaS Provider (Oracle) in a timely manner, then it may adversely impact Project timelines.

(e)	For defects discovered, in the Oracle Cloud ERP application, during the hyper-care post implementation support period, caused by and within the work performed by IBM, the IBM team will be responsible to:

a.	Resolve all Severity 1 defects and;

b.	Resolve or provide suitable CFMWS agreed workarounds for outstanding Severity 2 and Severity 3 defects

(f)	The parties acknowledge and agree that COVID-19 and/or other pandemics are events beyond the parties’ reasonable control, and it is not possible to foresee (or advisable to try and foresee) its duration, impact, or extent (including measures and recommendations that may be put in place by regulators). As such, where a party's non-monetary obligations are not performed, affected, and/or delayed and that is attributable to COVID-19, and/or other pandemics, or its related impacts, notwithstanding any other provision in the agreement, the affected party will not be responsible for such non-performance, affected performance or delay. The parties will act reasonably to discuss the affected obligations, potential workarounds and related issues in good faith and will document any agreed changes to the agreement.

(g)	IBM is not responsible for reasonably unforeseen delays in the schedule or additional costs incurred due to conditions where the cause or the resolution is outside of our direct control or accountability.

(h)	English will be the official language of the Project. All Project tasks, activities, communications, deliverables, work products and documents will be conducted / produced in English.

(i)	Our engagement team will have reasonable and expedient access to all systems documentation, identified Subject Matter Experts from CFMWS, business personnel, and other stakeholders that are relevant to this engagement. IBM will also have reasonable and expedient access to all identified company data and information that is relevant to this engagement, as the timeliness and quality of the deliverables may depend on such access. Where documentation is not available or obsolete, we will base our recommendations on clearly defined assumptions to be confirmed by the Project sponsor.

## IBM and CFMWS Roles and Responsibilities (RASCI)

The following section describes the Project activities based on IBM’s Oracle Rapid Move for Cloud Methodology by the expected Phase. Activities may be completed in other phases than where listed. The Project will follow a “RASCI” based governance model. This RASCI is not intended to define all activities required on the project. Additional activities not defined within the RASCI will be discussed between the Supplier and CFMWS but will not result in a Change Request if the activity is within scope for the services defined. The ‘RASCI’ is defined as follows:

Table 19: RASCI Definition

| Definitions |  |  |
| --- | --- | --- |
| Responsible | R | The group who “does the work" to complete the assigned activities and/or Deliverables |
| Accountable | A | The group to whom "R" is Accountable; the authority who approves/signs off activities and/or Deliverables |
| Support | S | The group who supports the work and actively contributes to activities, work products and/or Deliverables under the leadership and guidance of the “R” group |
| Consulted | C | The group whom “R” consults for input/expertise. Does not actively contribute and participate in activity, work product and/or Deliverable |
| Informed | I | The group notified of an activity and/or Deliverable status only |

The following activities will be completed during the Project.

Table 20: Delivery Phase Activities

| Area | Activity | CFMWS Responsibility |  |  |  |  | IBM Responsibility |  |  |  |  | Work Product / Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | R | A | S | C | I | R | A | S | C | I |  |
| Project Management | Kick Off Project & Mobilize Resources | X | X |  |  |  | X |  |  |  |  |  |
|  | Execute Project Management Processes Project Governance Change Control Deliverable Approval |  | X | X |  |  | X |  |  |  |  |  |
|  | Prepare Risk Assessment |  | X | X |  |  | X |  |  |  |  |  |
|  | Create & Manage Project Plan |  | X | X |  |  | X |  |  |  |  | Project Plan Updated (in MS Project) |
|  | Prepare Executive Committee Material | X | X |  |  |  |  |  | X |  | X |  |
|  | Develop Project Charter |  | X | X |  |  | X |  |  |  |  | Project Charter |
|  | Conduct IBM Oracle Rapid Move for Cloud Methodology Workshop |  |  | X |  |  | X |  |  |  |  |  |
|  | Create plan and manage Personal Identifiable Information (PII) for all project activities | X | X |  |  |  |  |  |  | X |  |  |
| Business Process | Create Requirements Traceability Matrix Template |  | X | X |  |  | X |  |  |  |  | Requirements Traceability Matrix Template |
|  | Finalize Business Requirements | X | X |  |  |  |  |  |  | X |  | User Stories Requirements Traceability Matrix |
|  | Create Business Process Workshop Plan / Schedule |  | X | X |  |  | X |  |  |  |  | Business Process Workshop Schedule |
|  | Schedule Business Process Workshops | X | X |  |  |  |  |  |  |  | X |  |
|  | Create Business Process Workshop Template |  | X | X |  |  | X |  |  |  |  | Business Process Workshop Template |
|  | Conduct Oracle Cloud ERP Familiarization Demonstration |  |  | X |  |  | X |  |  |  |  |  |
|  | Complete Oracle Cloud ERP Product Training (Core Team) [Prior to Business Process Workshops] | X | X |  |  |  |  |  |  |  | X |  |
|  | Conduct Business Process Adoption Workshops |  | X | X |  |  | X |  |  |  |  |  |
|  | Chart of Account Segment Value definitions | X | X |  |  |  |  |  |  | X |  | Chart of Account Segment Value Specifications |
|  | Develop L3 Business Processes |  | X | X |  |  | X |  |  |  |  |  |
|  | User Story Traceability Matrix | X | X |  |  |  |  |  | X |  | X |  |
| Application | Perform Application Fit/Gap |  | X | X |  |  | X |  |  |  |  | Application Fit/Gap and RICE identification |
|  | Prepare High-level Solution architecture |  | X | X |  |  | X |  |  |  |  | High-level Solution Architecture approach |
|  | Confirm 9 Levers of Scope |  | X | X |  |  | X |  |  |  |  | Updated 9 Levers of Scope Documented for Project Implementation |
|  | Provision Oracle Cloud Subscriptions for Discovery environment | X |  |  |  |  |  |  | X |  |  | Provide one Oracle Cloud ERP environment, by 15-May-2023, to support the Discovery phase and CRP0 |
|  | Provide PeopleSoft environments for Discovery | X |  |  |  |  |  |  | X |  |  | Provide one cloned instance of current PeopleSoft, to support the Discovery phase and Fit/Gap |
|  | Prepare Oracle Applications Instance Strategy [how environments will be utilized] |  | X | X |  |  | X |  |  |  |  | Oracle Application Instance Strategy |
|  | Setup Oracle Environment Instance for Business Process Workshops |  | X |  |  |  | X |  |  |  |  |  |
|  | Develop Application Security Strategy |  | X | X |  |  | X |  |  |  |  | Application Security Strategy (Including role-based access control and integration to LDAP) |
|  | Oracle ERP Cloud Application Design |  | X | X |  |  | X |  |  |  |  | Configuration Workbook |
|  | Configure Oracle Cloud Application |  | X | X |  |  | X |  |  |  |  |  |
|  | Security Roles Functional Design | X | X |  |  |  |  |  |  | X |  |  |
|  | Security Roles Technical Design |  | X |  | X |  | X |  |  |  |  |  |
|  | Build & Unit Test Security Roles |  | X |  | X |  | X |  |  |  |  |  |
|  | Define Role to User Mapping | X | X |  |  |  |  |  |  | X |  |  |
|  | Assign security roles to users |  | X | X |  |  | X |  |  |  |  |  |
|  | Validate end user security role assignment | X | X |  |  |  |  |  |  | X |  |  |
| Reports, Integrations, Extensions (RIE) | Provide sample reports with layouts, fields and filtering parameters. | X |  |  |  |  |  | X |  | X |  | Sample report layouts |
|  | Prepare Functional Designs for RIE (Reports, Interfaces, Extensions) |  | X | X |  |  | X |  |  |  |  | Functional Designs |
|  | Create Technical Specification Documents (TSD) |  | X | X |  |  | X |  |  |  |  | Technical Designs |
|  | Develop Reports, Interfaces and Extensions |  | X |  | X |  | X |  |  |  |  |  |
|  | Oracle Technical Unit Test Reports, Interfaces, Extensions |  | X |  | X |  | X |  |  |  |  |  |
|  | Oracle Batch Schedule Design |  | X | X |  |  | X |  |  |  |  | Batch Schedule Design |
|  | Create Batch Schedule (including integrations) |  | X | X |  |  | X |  |  |  |  | Batch Schedule created in Enterprise Scheduler |
| Infrastructure | Administer Oracle Integration Cloud and other Oracle PaaS integration tools and utilities | X | X |  |  |  |  |  |  | X |  |  |
|  | Administer Azure EAI, APIM and other Azure integration tools and utilities | X | X |  |  |  |  |  |  | X |  |  |
|  | Coordinate environment data refreshes | X | X |  |  |  |  |  |  | X |  |  |
|  | Manage Oracle Service Requests |  | X | X |  |  | X |  |  |  |  |  |
|  | Provision and Manage boundary-system Infrastructure | X | X |  |  |  |  |  |  | X |  |  |
|  | All patching and upgrade related activities for the SaaS applications | X | X |  |  |  |  |  |  | X |  |  |
|  | Perform Disaster Recovery (DR) and Business Continuity (BC) related activities for Oracle SaaS and PaaS | X | X |  |  |  |  |  |  | X |  |  |
|  | Provision and Manage PeopleSoft Infrastructure and CFMWS other legacy applications | X | X |  |  |  |  |  |  | X |  |  |
|  | Oracle SaaS Management |  |  |  |  |  |  |  |  |  |  |  |
|  | Oracle PaaS/IaaS (OCI) Management | X | X |  |  |  |  |  |  |  | X |  |
|  | MS Azure Cloud (PaaS & IaaS) Management | X | X |  |  |  |  |  |  |  | X |  |
|  | Oracle and Azure Connectivity Management | X | X |  |  |  |  |  |  |  | X |  |
|  | Oracle to CFMWS system(s) connectivity | X | X |  |  |  |  |  |  |  | X |  |
|  | Azure to CFMWS system(s) connectivity | X | X |  |  |  |  |  |  |  | X |  |
| Integration | Plan & Create schedule for Integration Workshops |  | X | X |  |  | X |  |  |  |  |  |
|  | Schedule Integration Workshops | X | X |  |  |  |  |  |  |  | X | Integration Review/Assessment workshop(s) scheduled |
|  | Conduct Integration Workshops |  | X | X |  |  | X |  |  |  |  | Technical Integration Requirements Inventory |
|  | Provide source data model, data flows, and transactional data rules | X | X |  |  |  |  |  |  | X |  |  |
|  | Identify 3rd party application impacts |  | X | X |  |  | X |  |  |  |  | Boundary system impacts |
|  | Prepare Integration Strategy |  | X | X |  |  | X |  |  |  |  | Integration Strategy (including process impacts, boundary system impacts, interim integrations, and final-state integrations) |
|  | Provide the data elements and business rules required to develop the integration design specifications for existing systems | X | X |  |  |  |  |  |  | X |  |  |
|  | Design boundary system data extraction for Inbound Interfaces | X | X |  |  |  |  |  |  |  | X | Legacy Integration Data Extracts |
|  | Design integration data transformation (mapping, logic) for Inbound Interfaces |  | X | X |  |  | X |  |  |  |  |  |
|  | Design Integration Data Load for Inbound Interfaces |  | X |  | X |  | X |  |  |  |  |  |
|  | Build & Unit Test data extraction from boundary systems for Inbound Interfaces | X | X |  |  |  |  |  |  | X |  |  |
|  | Build & Unit Test data transformation for Inbound Interfaces |  | X |  |  |  | X |  |  |  |  |  |
|  | Build & Unit Test data load for Inbound Interfaces |  | X |  |  |  | X |  |  |  |  |  |
|  | Design outbound interface data extraction |  | X | X |  |  | X |  |  |  |  |  |
|  | Design outbound interface data transformation (mapping, logic) |  | X | X |  |  | X |  |  |  |  |  |
|  | Design outbound interface data load to target system | X | X |  |  |  |  |  |  | X |  |  |
|  | Specify data and formats requirements for boundary system integration |  | X |  | X |  | X |  |  |  |  |  |
|  | Build & Unit Test outbound interface data extraction from Oracle ERP |  | X | X |  |  | X |  |  |  |  |  |
|  | Build & Unit Test outbound interface data transformation |  | X | X |  |  | X |  |  |  |  |  |
|  | Build & Unit Test outbound interface data load to target system | X | X |  |  |  |  |  |  | X |  |  |
|  | Boundary system Data Validation & Cleansing | X | X |  |  |  |  |  |  | X |  |  |
| Conversion | Conversion Requirement Gathering |  | X | X |  |  | X |  |  |  |  | Conversion Requirements List (incl. conversion objects) |
|  | Plan & create schedule for Conversion Workshops |  | X | X |  |  | X |  |  |  |  | Conversion Workshop Schedule |
|  | Schedule Conversion Workshops | X | X |  |  |  |  |  |  |  | X |  |
|  | Conduct Conversion Workshops |  | X | X |  |  | X |  |  |  |  |  |
|  | Prepare Data Cleanup Approach |  | X | X |  |  | X |  |  |  |  | Data Cleansing and Validation Strategy |
|  | Prepare Data Conversion Strategy |  | X | X |  |  | X |  |  |  |  | Data Conversion Strategy |
|  | Validation and sign-off of Data Conversion Strategy | X |  |  |  |  |  |  |  |  |  |  |
|  | Identification of Conversion Objects |  | X | X |  |  | X |  |  |  |  |  |
|  | Design Conversion Data Extraction | X | X | X |  |  |  |  |  |  |  | Functional Specifications (Data Migration) Deliverable |
|  | Design Conversion data transformation (mapping, logic) | X | X | X |  |  |  | X |  | X |  | Functional Specifications (Data Migration) Deliverable |
|  | Design Conversion data load |  | X |  | X |  | X |  |  |  |  | Functional Specifications (Data Migration) Deliverable |
|  | Execute Conversion Runs |  | X |  | X |  | X |  |  |  |  | Data Conversion Run Report (CNV1) Deliverable |
|  | Manual data conversions | X | X |  |  |  |  |  |  | X |  |  |
|  | Validate Conversion Run Results and Sign-off on converted data | X | X |  |  |  |  |  |  | X |  |  |
|  | Cleanse Data in source systems | X | X |  |  |  |  |  |  |  | X |  |
|  | Execute full production data conversion |  | X | X |  |  | X |  |  |  |  | Full Volume Conversion Run Report |
| Testing | Prepare Testing Strategy |  | X | X |  |  | X |  |  |  |  | Test Strategy (All Test Phases including Test Automation) |
|  | Prepare System and Integration Test (SIT) Testing Plan (incl. cross-application end-to-end tests) | X | X |  |  |  |  |  |  | X |  | System Integration Test Plan |
|  | Develop SIT Test Scripts (incl. cross-application end-to-end tests) | X | X |  |  |  |  |  |  | X |  |  |
|  | Prepare Test Data for System Integration Testing (incl. boundary system data) | X | X |  |  |  |  |  |  | X |  |  |
|  | Execute SIT Test Scripts (incl. cross-application end-to-end tests) | X | X |  |  |  |  |  |  | X |  | System Integration Test Execution Report |
|  | Execute boundary system integration testing (including external systems) | X | X |  |  |  |  |  |  | X |  |  |
|  | Resolve SIT defects / issue in Oracle |  | X |  | X |  | X |  |  |  |  |  |
|  | Resolve SIT defects / issue in other boundary systems | X | X |  |  |  |  |  |  | X |  |  |
|  | Plan User Acceptance Test (UAT) | X | X |  |  |  |  |  |  | X |  | UAT Plan |
|  | Develop UAT Test Scripts | X | X |  |  |  |  |  |  | X |  |  |
|  | Prepare Test Data for UAT | X | X |  |  |  |  |  |  | X |  |  |
|  | Conduct UAT | X | X |  |  |  |  |  |  | X |  | UAT Execution Report |
|  | Resolve UAT Defects in Oracle |  | X | X |  |  | X |  |  |  |  |  |
|  | Resolve UAT Defects in other boundary systems | X | X |  |  |  |  |  |  | X |  |  |
|  | Identify Training Data Requirements (based on UAT scenarios to be used in training exercises) |  | X |  | X |  | X |  |  |  |  | Training Data Requirement |
|  | Prepare Data for Training | X | X |  |  |  |  |  |  | X |  |  |
| OCM & Training | Executive Alignment - Envision Studio |  | X | X |  |  | X |  |  |  |  | Program Vision agreed |
|  | Stakeholder Assessment | X | X |  |  |  |  |  |  | X |  | Identified Stakeholders |
|  | Change Management Strategy | X | X |  |  |  |  |  |  | X |  |  |
|  | Change Impact Assessment |  | X | X |  |  | X |  |  |  |  | High level change impacts |
|  | Change Transition Plan | X | X |  |  |  | X |  |  | X |  |  |
|  | Communication needs assessment |  | X |  | X |  | X |  |  |  |  | Communication plan |
|  | Communications Plan | X | X |  |  |  | X |  |  | X |  |  |
|  | Deliver Stakeholder Communications | X | X |  |  |  |  |  | X |  |  |  |
|  | Develop and Evaluate Communication Pulse Checks | X | X |  |  |  |  |  | X |  |  |  |
|  | Change Readiness Assessment | X | X |  |  |  |  |  |  | X |  |  |
|  | Change Champions | X | X |  |  |  |  |  |  | X |  |  |
|  | Develop Change Network Sessions | X | X |  |  |  |  |  |  | X |  |  |
|  | Create Organizational Readiness Transition Scorecard | X | X |  |  |  |  |  |  | X |  |  |
|  | Training Needs Assessment |  | X |  | X |  | X |  |  |  |  | Training Needs Assessment completed |
|  | Training Strategy & Plan |  | X |  | X |  | X |  |  |  |  | Training Strategy & Plan created |
|  | Training Curriculum |  | X |  | X |  | X |  |  | X |  | Training curriculum completed |
|  | Training Materials (Oracle Guided Learning) |  | X |  |  |  | X |  |  | X |  | Access to OGL established and CFMWS onboarded to OGL |
|  | Training Material – Job Aids / QRG and TTT Module specific introductions |  |  |  | X |  | X |  |  |  |  | Module introduction ppt created for TTT. Quick Reference Guides (QGR) completed |
|  | Prepare Data for Training Environment |  | X |  | X |  | X |  |  | X |  | Training Environment ready for TTT |
|  | Train-the-Trainer |  | X |  | X |  | X |  |  |  |  |  |
|  | Develop Training Logistics Plan | X | X |  |  |  |  |  |  |  | X | Training Logistics Plan |
|  | Manage Training Logistics | X | X |  |  |  |  |  |  |  | X |  |
|  | End User Training Delivery | X | X |  |  |  |  |  |  | X |  |  |
|  | Evaluate Training effectiveness | X | X |  |  |  |  |  |  |  | X | Training Effectiveness Scorecard |
|  | Knowledge Transfer (KT) Approach and Plan |  | X |  | X |  | X |  |  |  |  | KT approach and plan created |
| Transition | Create Transition Strategy |  | X | X |  |  | X |  |  |  |  | Transition Strategy |
|  | Create Managed Services Transition Plan |  | X | X |  |  | X |  |  |  |  | Managed Services Transition Plan |
|  | Create Knowledge Transfer Documentation | X | X |  |  |  |  |  |  | X |  | Knowledge Transfer Materials |
|  | Create Solution Readiness Dashboard |  | X |  | X |  | X |  |  |  |  | Solution Readiness Dashboard |
|  | Plan Go-Live (Cutover) Dress Rehearsal [including Backout] |  | X |  | X |  | X |  |  |  |  | Dress Rehearsal Plan |
|  | Execute Go-Live (Cutover) Dress Rehearsal |  | X |  | X |  | X |  |  |  |  | Dress Rehearsal Results Summary |
|  | Create Organization Readiness Survey |  | X | X |  |  | X |  |  |  |  |  |
|  | Conduct Organization Readiness Survey |  | X | X |  |  | X |  |  |  |  |  |
|  | Prepare Organization for Production Cutover | X | X |  |  |  |  |  |  | X |  |  |
|  | Create Production Cutover Plan (Oracle) |  | X |  | X |  | X |  |  |  |  | Production Cutover Plan |
|  | Create Production Cutover Plan (other CFMWS systems) and Business Cutover Plan | X | X |  |  |  |  |  |  | X |  | Production Cutover Plan (Other CFMWS Systems) |
|  | Prepare Decommissioning Plan | X | X |  |  |  |  |  |  |  | X | Decommissioning Plan |
|  | Prepare Hypercare Support Plan |  | X | X |  |  | X |  |  |  |  | Hypercare Support Plan |
|  | Implementation Go / No Go Decision |  | X | X |  |  | X |  |  |  |  | Go / No Go Decision Document |
|  | Execute the Production Cutover Plan (Oracle) |  | X | X |  |  | X |  |  |  |  | Cutover Results Summary |
|  | Execute the Production Cutover Plan (other CFMWS systems) and Business Cutover Plan | X | X |  |  |  |  |  |  |  | X |  |
|  | Operate Live Oracle ERP Application | X | X |  |  |  | X |  |  |  |  |  |
| Realization | Execute Hypercare Support Plan |  | X | X |  |  | X |  |  |  |  | Weekly Hypercare Reports |
|  | Post Go-Live Support - Troubleshoot issues and incidents | X | X |  |  |  | X |  |  |  |  |  |
|  | Decommission legacy applications | X | X |  |  |  |  |  |  |  | X | Retired PeopleSoft Systems |
|  | Close Project | X | X |  | X |  | X |  |  |  |  | Project Closure Report |

Boundary System: a system, internal within WSIB or external, that has one or more integration points with Oracle Fusion

Inbound interface: an interface / integration where the data flows from a boundary system into Oracle Fusion

Inbound interface: an interface / integration where the data flows out from Oracle Fusion to a boundary system.